## Project Plan and Gantt
Project Name | Virtualines Service App |  |  |  |  | Virtualines has over 1000 clients in Excel sheet. They offer file distribution services. The CEO ( John Doe ) wants a web application built for his company. He wants an online database with his customers who can login and a registration form for new customers. There should be basic and premium Membership for his clients. He wants Employers to have a dashboard for managing clients. He wants a search / sorting system based on location and certian keywords. He wants to processing Client payment realtime and verify the payment as well as keep the orders for transaction processing purposes. He wants a dashboard for his clients to manage their profiles and orders. He wants to avoid so many pages so the web application must be simple. He wants a feature for Messaging clients and attaching additional files.
Project Sponsor | John Doe
Project Deliverable | A web application
Scope Statement:
Start Date | 2016-09-01
End Date | 2016-09-21
Overall Progress
Tasks | Responsible | Start | End | Days | Status |  | Gannt Chart / Progress Tracking
Set kick-off meeting |  | 2016-09-01 | 2016-09-02 | 1 | Complete
Agree on objectives |  | 2016-09-02 | 2016-09-04 | 2 | Complete
Detailed Reqs. |  | 2016-09-04 | 2016-09-05 | 1 | Complete
Staffing / Resources |  | 2016-09-05 | 2016-09-06 | 1 | Canceled
Design |  | 2016-09-06 | 2016-09-08 | 2 | In progress
Front-End Coding |  | 2016-09-07 | 2016-09-09 | 2 | In progress
DB Creation |  | 2016-09-09 | 2016-09-10 | 1 | Not started
Helper Function |  | 2016-09-10 | 2016-09-11 | 1 | Not started
Classes PDO |  | 2016-09-11 | 2016-09-12 | 1 | Not started
Back-End Coding |  | 2016-09-12 | 2016-09-15 | 3 | Not started
API Integration |  | 2016-09-15 | 2016-09-16 | 1 | Not started
Submit for Approval |  | 2016-09-16 | 2016-09-17 | 1 | Not started
Final Development |  | 2016-09-17 | 2016-09-19 | 2 | Not started
Testing |  | 2016-09-19 | 2016-09-20 | 1 | Not started
Launch |  | 2016-09-20 | 2016-09-21 | 1

## Stakeholder List
Stakeholder List / Sponser
Name | Position | Role in project | Email address | Expectations
John Doe | CEO of Product | Final approval | jdoe@virtualines.com | A fully functional web application for virtualines that sells files and manages clients
Jennet Smith | Senior Manager | Milestone aproval | jsmith@virtualines.com | Web application working in line with company objectives and mission

## Cost Baseline
Project Cost Baseline
Item/task | % Complete | Base Cost | Cost | % Budget Spent
Hardware Setup | 50% | 800 | 1000 | 45%
Hosting and Maintenance | 0% | 100 | 120 | 5.4%
API Integration | 0% | 200 | 300 | 13.6%
Design Workmanship | 0% | 200 | 300 | 13.5%
Coding Workmanship | 0% | 500 | 500 | 22.5%
|  | 1800 | 2220 | 100%